## summer_2023_prep
Date | Event | Personnel | Status | Priority | Notes
2022-02-28 | Email volunteers and collaborators general announcement; save the date | BM | done
2022-03-15 | Receive example test kit from SGS | BM |  |  | probably not necessary
2022-03-21 | Inventory neeed for gloves and ziplocs | BM |  |  | order more for summer 2023
2022-03-23 | Email volunteers and collaborators further detailed plans. Confirm sampling teams. | BM | done
2022-03-25 | Order full kits from SGS | BM | done
2022-03-25 | Get ice packs for sample storage if not from SGS | BM
2022-04-11 | Send site names list to SGS
2022-04-11 | Confirm with SGS that trip blanks are assign-able to site names
2022-07-01 | Print waterproof labels | BM
2022-07-18 | Prep/Assemble sampling cooler contents | BM
2022-07-18 | Confirm/double check cooler content | BM
2022-07-18 | Send one week reminder. | BM
2022-07-19 | Follow up on emails from anyone who did not reply | BM
2022-07-25 | Disperse sampling kits & training | BM
2022-07-26 | Sampling day | BM
2022-07-26 | Order lunch for volunteers | RM
2022-07-26 | Transport Fecal Coliform and Total Suspended Solids to soldotna wastewater plant | BB
2022-07-26 | Transport SGS samples to Kenai Airport | BM
2022-07-01 | Prepare Chain of Custody forms for SGS and SWWTP | BM |  |  | make clear we need signed copies back
Complete KRBWQM fact sheet, print ~40x copies
Assess needs for "group" training class
2022-07-01 | Print off sampling instructions for volunteers | BM
2022-07-01 | Re-do field data forms for summer 2021 based on feedback to conform with tidy data standards

## summer_2023_kit_contents
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes | Training / Pickup Date
Salamatof / KWF | RM 0 - No Name Creek | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SGS | x
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SWWTP | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP | x
| RM 0 - No Name Creek - DUP | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SGS | x
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SWWTP | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP | x
| RM 1.5 - Kenai City Dock | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SGS | x
|  | Bottle | 125 mL HDPE | 2 | None | 200.8 - Dissolved Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SWWTP | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP | x
|  | Vial | 40 mL VOA glass vial | 3 | HCl | 624 - BTEX
|  | Bottle | 1 L HDPE | 1 |  | Source purified H2O
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2
Salamatof / KWF |  | Gloves (pair) |  | 7
|  | Packing List |  | 1
|  | Clipboard/Forms |  | 1
|  | Instructions |  | 1
|  | Labels |  | 1
|  | Temperature Probe |  | 1
[8 empty] | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
[8 empty] | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
x
x
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | x
USFWS | RM 6.5 - Cunningham Park | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Vial | 40 mL VOA glass vial | 3 | HCl | 624 - BETX |  | x
|  | Vial | 40 mL VOA glass vial | 3 | HCl | 624 - BTEX Trip Blank |  | x
x
| RM 10 - Beaver Creek | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals |  | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
| RM 10 - Beaver Creek | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | x
USFWS | RM 10.1 - Kenai River | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals |  | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | x
x
| RM 12.5 - Pillars | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals |  | x
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | x
USFWS | RM 12.5 - Pillars | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | x
| RM 18 - Poachers Cove | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
|  | Gloves (pair) |  | 12
|  | Packing List |  | 1 |  |  |  | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
|  | Clipboard/Forms |  | 1 |  |  |  | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Instructions |  | 1 |  |  |  | SGS | x
|  | Labels |  | 1 |  |  |  | SGS | x
|  | Temperature Probe |  | 1 |  |  |  | SWWTP | x
[8 empty] | SWWTP | x
[8 empty] | SGS | x
[8 empty] | SGS | x
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | SWWTP | x
CIAA / KWF | RM 19 - Slikok Creek | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SWWTP | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SGS | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SGS | x
[8 empty] | SWWTP | x
| RM 21 - Soldotna Bridge | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SWWTP | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 2 | None | 200.8 - Dissolved Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SGS | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SGS | x
|  | Bottle | 1 L HDPE | 1 |  | Source purified H2O
[8 empty] | SWWTP | x
| RM 22 - Soldotna Creek | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SWWTP | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 23 - Swiftwater Park | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2
CIAA / KWF | RM 23 - Swiftwater Park | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SGS | x
[8 empty] | SGS | x
|  | Gloves (pair) |  | 10 |  |  |  | SGS | x |  |  |  | No further sites upstream for dissolved metals
|  | Packing List |  | 1 |  |  |  | SWWTP | x
|  | Clipboard/Forms |  | 1 |  |  |  | SWWTP | x
|  | Instructions |  | 1
|  | Labels |  | 1 |  |  |  | SGS | x
|  | Temperature Probe |  | 1 |  |  |  | SGS | x
[8 empty] | SWWTP | x
[8 empty] | SWWTP | x
[8 empty] | SGS | x
[8 empty] | SGS | x
[8 empty] | SWWTP | x
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | SWWTP | x
TU / KWF | RM 30 - Funny River | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | None | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 31 - Morgan's Landing | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
[8 empty] | SGS | x
| RM 36 - Moose River | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SWWTP | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SWWTP | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 36 - Moose River-DUP | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SWWTP | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP | x
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2
TU / KWF |  | Gloves (pair) |  | 10
|  | Packing List |  | 1
|  | Clipboard/Forms |  | 1 |  |  |  | SGS | x
|  | Instructions |  | 1 |  |  |  | SGS | x
|  | Labels |  | 1 |  |  |  | SWWTP | x
|  | Temperature Probe |  | 1 |  |  |  | SWWTP | x
[8 empty] | SGS | x
[8 empty] | SGS | x
[8 empty] | SWWTP | x
[8 empty] | SWWTP | x
[8 empty] | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | SGS
DEC/DNR | RM 40 - Bing's Landing | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SWWTP
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SWWTP
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
|  | Vial | 40 mL VOA glass vial | 3 | HCl | 624 - BETX |  | SGS
|  | Vial | 40 mL VOA glass vial | 3 | HCl | 624 - BTEX Trip Blank |  | SGS
SWWTP
| RM 43 - Upstream of Dow Island | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SWWTP
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SGS
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SGS
|  | Vial | 40 mL VOA glass vial | 3 | HCl | 624 - BTEX |  | SWWTP
|  | Vial | 40 mL VOA glass vial | 3 | HCl | 624 - BTEX Trip Blank |  | SWWTP
| RM 44 - Mouth of Killey River | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SGS
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SWWTP
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP
| RM 50 - Skilak Lake Outflow | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2
DEC/DNR | RM 50 - Skilak Lake Outflow | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
|  | Gloves (pair) |  | 10
|  | Packing List |  | 1
|  | Clipboard/Forms |  | 1 |  |  |  | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
|  | Instructions |  | 1 |  |  |  | SGS
|  | Labels |  | 1 |  |  |  | SGS
|  | Temperature Probe |  | 1 |  |  |  | SGS
SWWTP
SWWTP
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2
USFS | RM 70 - Jim's Landing | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 74 - Russian River | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 82 - Kenai Lake Bridge | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 79.5 - Juneau Creek | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
|  | Gloves (pair) |  | 10
|  | Packing List |  | 1
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2
USFS |  | Clipboard/Forms |  | 1
|  | Instructions |  | 1
|  | Labels |  | 1
|  | Temperature Probe |  | 1
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2
Office | Spare Kit | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
|  | Gloves (pair) |  | 10
|  | Packing List |  | 1
|  | Clipboard/Forms |  | 1
|  | Instructions |  | 1
|  | Labels |  | 1
|  | Temperature Probe |  | 1

## site_names
RM 0 - No Name Creek
RM 0 - No Name Creek - DUP
RM 1.5 - Kenai City Dock
RM 6.5 - Cunningham Park
RM 10 - Beaver Creek
RM 10.1 - Kenai River
RM 12.5 - Pillars
RM 18 - Poachers Cove
RM 19 - Slikok Creek
RM 21 - Soldotna Bridge
RM 22 - Soldotna Creek
RM 23 - Swiftwater Park
RM 23 - Swiftwater Park
RM 30 - Funny River
RM 31 - Morgan's Landing
RM 36 - Moose River
RM 36 - Moose River-DUP
RM 40 - Bing's Landing
RM 43 - Upstream of Dow Island
RM 44 - Mouth of Killey River
RM 50 - Skilak Lake Outflow
RM 50 - Skilak Lake Outflow
RM 70 - Jim's Landing
RM 74 - Russian River
RM 82 - Kenai Lake Bridge
RM 79.5 - Juneau Creek
Site
Site
Spare Kit

## kit_content_summary
Row Labels | Sum of Quantity
Bottle | 118
1 L HDPE | 27
None | 25
1 liter Total Suspended Solids | 25
(blank) | 2
Source purified H2O | 2
125 mL HDPE | 41
HNO3 | 26
200.7 - Total Metals | 25
200.8 - Dissolved Metals | 1
None | 15
200.8 - Dissolved Metals | 15
250 mL HDPE | 25
H2SO4 | 25
SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | 25
Sterile 120 mL | 25
Na2S2O3 | 25
Fecal Coliform | 25
Clipboard/Forms | 7
(blank) | 7
(blank) | 7
1
(blank) | 6
Gloves (pair) | 69
(blank) | 69
(blank) | 69
(blank) | 69
Instructions | 7
(blank) | 7
(blank) | 7
(blank) | 7
Labels | 7
(blank) | 7
(blank) | 7
(blank) | 7
Packing List | 7
(blank) | 7
(blank) | 7
(blank) | 7
Temperature Probe | 7
(blank) | 7
(blank) | 7
(blank) | 7
(blank)
(blank)
(blank)
(blank)
Vial | 21
40 mL VOA glass vial | 21
HCl | 21
624 - BTEX | 3
624 - BTEX Trip Blank | 9
624 - BETX | 6
624 - BTEX | 3
Item | 0
Container/Size | 0
Preservative | 0
Analysis 1 | 0
Grand Total | 243

## sample_types
Test | Spring_Analysis | Summer_Analysis
Dissolved metals | SGS North America | SGS North America
Total metals | SGS North America | SGS North America
Total Phosphorous | SGS North America | SGS North America
Nitrogen | SGS North America | SGS North America
BTEX (hydrocarbons) | NONE | SGS North America
TSS | Soldotna Water Quality Tx Plant | Soldotna Water Quality Tx Plant
Fecal coliform | Soldotna Water Quality Tx Plant | Tauriainen

## sample_day_info
Info Category | Parameter | Value | Notes
Environmental | High Tide July 18 | 5:15 | 19.9
Environmental | Low Tide July 18 | 12:49 | -1.9
Sampling Sites | Hydrocarbon sampling sites | 4 | use same 4 sites as 2020
Sampling Sites | Metals sampling sites |  | collect below RM 30 only

## training_notes
Remind and prep to collect intrinsic parameters
Duplicate samples rotate among sites and teams
Drop off coolers if passing by KWF office

## summer_2023_crew_assignments
Summer 2023 Water Quality Sampling Crews
River Mile | Location / Sample Name | Mainstem | Tributary | Samplers/Teams | Date | Time | Training scheduled?
0 | No Name Creek |  | x | Yvonne Weber + Ciara Bismarck (Salamatof) + 1 Kenaitze intern |  |  | Y
1.5 | No Name Creek - DUP | x
1.5 | Kenai City Dock | x |  | Has field blank sample for diss metals
6.5 | Cunningham Park | x |  | Kyle Graham (USFWS; boat driver) + 2 USFWS personnel |  |  | Y
10 | Beaver Creek |  | x
10.1 | Kenai River | x
12.5 | Pillars | x
18 | Poachers Cove | x
19 | Slikok Creek |  | x | Cook Inlet Aquaculture Association [Emily Heale + 1 Staff] |  |  | Y
21 | Soldotna Bridge | x |  | Has field blank sample for diss metals
22 | Soldotna Creek |  | x
23 | Swiftwater Park | x
30 | Funny River |  | x | [KWF Staff TBD] + Alexa Millward [TU Alaska]
31 | Morgan’s Landing | x
36 | Moose River | x
36 | Moose River-DUP |  | x
40 | Bing’s Landing | x |  | Jenny Petit (ADEC); Nick Jacuk (UAF); Avery Hansen (DNR; boat driver) |  |  | Y
43 | Upstream of Dow Island | x
44 | Mouth of Killey River |  | x
50 | Skilak Lake Outflow | x
70 | Jim’s Landing | x |  | USFS (2 Personnel TBD) |  |  | Y
74 | Russian River |  | x
79.5 | Juneau Creek |  | x
82 | Kenai Lake Bridge | x
Available Times for Training and Supplies Pickup Summer 2023. (Choose One)
sent confirmation email
Date | Time
2023-07-10 | 9:00 - 10:00 | Bonnie & Vic |  |  | y
10:00 - 11:00
11:00 - 12:00
12:00 - 1:00
1:00 - 2:00
3:00 - 4:00
4:00 - 5:00
2023-07-11 | 9:00 - 10:00
10:00 - 11:00
11:00 - 12:00
12:00 - 1:00
1:00 - 2:00
3:00 - 4:00
4:00 - 5:00
2023-07-12 | 9:00 - 10:00
10:00 - 11:00
11:00 - 12:00
12:00 - 1:00
1:00 - 2:00
3:00 - 4:00
4:00 - 5:00
2023-07-13 | 9:00 - 10:00 | jenny petit, nick jacuk + avery |  |  | Y
10:00 - 11:00
| 11:00 - 12:00 | Alexa Millward
12:00 - 1:00
1:00 - 2:00
3:00 - 4:00
4:00 - 5:00
2023-07-17 | 9:00 - 10:00 | sarah apsens, CIAA (trenten schipper and lisa k) |  |  | Y
10:00 - 11:00
11:00 - 12:00
| 12:00 - 1:00 | Alex palombo |  |  | Y
1:00 - 2:00
3:00 - 4:00
| 4:00 - 5:00 | yvonne weber + ciara bismark + matt + finn |  |  | Y

## random_site_assigner
site | random_num | sort_num | metals_field_blank | Task: randomly assign sites below RM 30 for field blanks
RM 21 - Soldotna Bridge | 0.61639 | 0.047617 | Y | Methods for choosing a random row: https://www.statology.org/random-sample-google-sheets/
RM1.5-DUP | 0.83736 | 0.087794 |  | 4/19/2023: decided to reassign RM 10.1 field blank to Pillars (RM12.5), unclear if 10.1 will be acessible
RM 6.5 - Cunningham Park | 0.38837 | 0.16064
RM 18 - Poachers Cove | 0.44549 | 0.1795
RM 23 - Swiftwater Park | 0.45936 | 0.23155
RM 10 - Beaver Creek | 0.84507 | 0.35712
RM 10.1 - Kenai River | 0.15871 | 0.41211
RM 12.5 - Pillars | 0.23273 | 0.43528
RM 19 - Slikok Creek | 0.55271 | 0.475
RM 30 - Funny River | 0.66132 | 0.52509
RM0 | 0.56275 | 0.78321
RM 22 - Soldotna Creek | 0.65899 | 0.7884
RM1.5 | 0.013938 | 0.88827 | Y