## spring_2023_prep
Date | Event | Personnel | Status | Priority | Notes
2023-02-28 | Email volunteers and collaborators general announcement; save the date | BM | done
2023-03-15 | Receive example test kit from SGS | BM |  |  | probably not necessary
2023-03-21 | Inventory neeed for filters, filters, syringes, and gloves | BM |  |  | order more for summer 2022
2023-03-23 | Email volunteers and collaborators further detailed plans. Confirm sampling teams. | BM | done
2023-03-25 | Modify field SOP to include field blank for metals | BM | done | High
2023-03-25 | Order full kits from SGS | BM | done |  | INCLUDE ULTRAPURE DISTILLED WATER FOR FIELD BLANKS. Not all sites, review apsens & petit 2022
2023-03-25 | Get ice packs for sample storage if not from SGS | BM | done
2023-04-11 | Send site names list to SGS
2023-04-11 | Confirm with SGS that trip blanks are assign-able to site names |  |  |  | This step applies only in summer, when trip blanks are used for BTEX
2023-04-11 | Print waterproof labels | BM
2023-04-13 | Prep/Assemble sampling cooler contents | BM
2023-04-15 | Confirm/double check cooler content | BM
2023-04-24 | Send one week reminder. Also try to confirm Summer 2022 personnel | BM
2023-04-27 | Follow up on emails from anyone who did not reply | BM
2023-05-01 | Disperse sampling kits | BM
2023-05-02 | Sampling day | BM
2023-05-03 | Order lunch for volunteers | RM
2023-05-03 | Transport Fecal Coliform and Total Suspended Solids to soldotna wastewater plant | BB
2023-05-03 | Transport SGS samples to Kenai Airport | BM
Complete filming for KRBWQM sampling methods vids
Publish youtube instructional vids
2023-04-05 | Prepare Chain of Custody forms for SGS and SWWTP | BM |  |  | make clear we need signed copies back
Complete KRBWQM fact sheet, print ~40x copies
Assess needs for "group" training class
| Print off sampling instructions for volunteers | BM
Re-do field data forms for summer 2021 based on feedback to conform with tidy data standards

## spring_2023_kit_contents
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
Salamatof, UAF | RM 0 - No Name Creek | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses | 27
|  | Bottle | 125 mL HDPE | 2 | HNO3 | 200.7 - Total Metals |  | SGS | x |  |  |  |  | 16
|  | Bottle | 125 mL HDPE | 2 | HNO3 | 200.8 - Dissolved Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SWWTP | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP | x
|  | Bottle | Ultrapure Distilled H2O |  | None | None - source for metals field blank
| RM 1.5 - Kenai City Dock | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SGS | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SWWTP | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP | x
| RM 1.5 - Kenai City Dock-DUP | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SGS | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SWWTP | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP | x
|  | Gloves (pair) |  | 8
|  | Packing List |  | 1
|  | Clipboard/Forms |  | 1
|  | Instructions |  | 1
|  | Labels |  | 1
|  | Temperature Probe |  | 1
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
KWF - Beaver Creek | RM 10 - Beaver Creek | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 10.1 - Kenai River | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
|  | Gloves (pair) |  | 8
|  | Packing List |  | 1
|  | Clipboard/Forms |  | 1
|  | Instructions |  | 1
|  | Labels |  | 1
|  | Temperature Probe |  | 1
[8 empty] | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
[8 empty] | SGS | x
[8 empty] | SGS | x
[8 empty] | SWWTP | x
[8 empty] | SWWTP | x
[8 empty] | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | SGS | x
KWF, TTCD | RM 6.5 - Cunningham Park | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SWWTP | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals |  | SWWTP | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
[8 empty] | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
[8 empty] | SGS | x
| RM 12.5 - Pillars | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS | x
|  | Bottle | 125 mL HDPE | 2 | HNO3 | 200.7 - Total Metals |  | SWWTP | x
|  | Bottle | 125 mL HDPE | 2 | HNO3 | 200.8 - Dissolved Metals |  | SWWTP | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
|  | Bottle | Ultrapure Distilled H2O |  | None | None - source for metals field blank
| RM 18 - Poachers Cove | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
[8 empty] | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Gloves (pair) |  | 10 |  |  |  | SGS | x
|  | Packing List |  | 1 |  |  |  | SGS | x
|  | Clipboard/Forms |  | 1 |  |  |  | SWWTP | x
|  | Instructions |  | 1 |  |  |  | SWWTP | x
|  | Labels |  | 1
|  | Temperature Probe |  | 1 |  |  |  | SGS | x
[8 empty] | SGS | x
[8 empty] | SGS | x
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | SWWTP | x
KPB | RM 19 - Slikok Creek | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SGS | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SGS | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP | x
[8 empty] | SWWTP | x
| RM 21 - Soldotna Bridge | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SGS | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals |  | SGS | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SGS | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP | x
[8 empty] | SWWTP | x
| RM 22 - Soldotna Creek | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 23 - Swiftwater Park | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals |  | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SGS | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SGS | x
[8 empty] | SGS | x |  |  |  | No further sites upstream for dissolved metals
|  | Gloves (pair) |  | 12 |  |  |  | SWWTP | x
|  | Packing List |  | 1 |  |  |  | SWWTP | x
|  | Clipboard/Forms |  | 1
|  | Instructions |  | 1 |  |  |  | SGS | x
|  | Labels |  | 1 |  |  |  | SGS | x
|  | Temperature Probe |  | 1 |  |  |  | SWWTP | x
[8 empty] | SWWTP | x
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | SGS | x
CIAA, Kenaitze | RM 30 - Funny River | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SGS | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SWWTP | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals |  | SWWTP | x
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SGS | x
[8 empty] | SGS | x
| RM 31 - Morgan's Landing | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SWWTP | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SWWTP | x
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 36 - Moose River | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 36 - Moose River-DUP | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
|  | Gloves (pair) |  | 12
|  | Packing List |  | 1
|  | Clipboard/Forms |  | 1
|  | Instructions |  | 1
|  | Labels |  | 1
|  | Temperature Probe |  | 1
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2
KWF - Skilak / Bing's | RM 40 - Bing's Landing | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 50 - Skilak Lake Outflow | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SGS | x |  |  |  | lab test uses same bottle for both Nitrogen and Phosphorus analyses
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SGS | x
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SWWTP | x
|  | Gloves (pair) |  | 10
|  | Packing List |  | 1 |  |  |  | SGS | x
|  | Clipboard/Forms |  | 1 |  |  |  | SGS | x
|  | Instructions |  | 1 |  |  |  | SWWTP | x
|  | Labels |  | 1 |  |  |  | SWWTP | x
|  | Temperature Probe |  | 1
[8 empty] | SGS | x
[8 empty] | SGS | x
[8 empty] | SWWTP | x
[8 empty] | SWWTP | x
[8 empty] | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
SGS
SGS
SWWTP
SWWTP
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2 | SGS
KWF - Dow Island, Killey | RM 43 - Upstream of Dow Island | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SWWTP
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals |  | SWWTP
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SGS
SGS
SWWTP
| RM 44 - Mouth of Killey River | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus | SWWTP
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids |  | SGS
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform |  | SGS
SWWTP
SWWTP
|  | Gloves (pair) |  | 10
|  | Packing List |  | 1
|  | Clipboard/Forms |  | 1
|  | Instructions |  | 1
|  | Labels |  | 1
[8 empty] | Analysis Lab | Prerecorded on Chain of Custody Form | Deposited in kit | Label Designed | Label Printed | Notes
SGS
SGS
SGS
SWWTP
SWWTP
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2
USFS | RM 70 - Jim's Landing | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 74 - Russian River | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 82 - Kenai Lake Bridge | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
| RM 79.5 - Juneau Creek | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
|  | Gloves (pair) |  | 12
|  | Packing List |  | 1
|  | Clipboard/Forms |  | 1
|  | Instructions |  | 1
|  | Labels |  | 1
|  | Temperature Probe |  | 1
Cooler Name | Site | Item | Container/Size | Quantity | Preservative | Analysis 1 | Analysis 2
Office | Spare Kit | Bottle | 250 mL HDPE | 1 | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | SM4500-PE - Total Phosphorus
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.7 - Total Metals
|  | Bottle | 125 mL HDPE | 1 | HNO3 | 200.8 - Dissolved Metals
|  | Bottle | 1 L HDPE | 1 | None | 1 liter Total Suspended Solids
|  | Bottle | Sterile 120 mL | 1 | Na2S2O3 | Fecal Coliform
|  | Gloves (pair) |  | 10
|  | Packing List |  | 1
|  | Clipboard/Forms |  | 1
|  | Instructions |  | 1
|  | Labels |  | 1
|  | Temperature Probe |  | 1

## site_names
RM 0 - No Name Creek
RM 1.5 - Kenai City Dock
RM 1.5 - Kenai City Dock-DUP
RM 6.5 - Cunningham Park
RM 10 - Beaver Creek
RM 10.1 - Kenai River
RM 12.5 - Pillars
RM 18 - Poachers Cove
RM 19 - Slikok Creek
RM 21 - Soldotna Bridge
RM 22 - Soldotna Creek
RM 23 - Swiftwater Park
RM 30 - Funny River
RM 31 - Morgan's Landing
RM 36 - Moose River
RM 36 - Moose River-DUP
RM 40 - Bing's Landing
RM 43 - Upstream of Dow Island
RM 44 - Mouth of Killey River
RM 50 - Skilak Lake Outflow
RM 70 - Jim's Landing
RM 74 - Russian River
RM 82 - Kenai Lake Bridge
RM 79.5 - Juneau Creek
Spare Kit

## kit_content_summary
Item | Container/Size | Preservative | Analysis 1 | Sum of Quantity
Bottle | 1 L HDPE | None | 1 liter Total Suspended Solids | 25
|  | None Total |  | 25
| 1 L HDPE Total |  |  | 25
| 125 mL HDPE | HNO3 | 200.7 - Total Metals | 27
|  |  | 200.8 - Dissolved Metals | 17
|  | HNO3 Total |  | 44
| 125 mL HDPE Total |  |  | 44
| 250 mL HDPE | H2SO4 | SM4500-NO3E - Nitrogen (Nitrate+Nitrite) | 25
|  | H2SO4 Total |  | 25
| 250 mL HDPE Total |  |  | 25
| Sterile 120 mL | Na2S2O3 | Fecal Coliform | 25
|  | Na2S2O3 Total |  | 25
| Sterile 120 mL Total |  |  | 25
| Ultrapure Distilled H2O | None | None - source for metals field blank
None Total
Ultrapure Distilled H2O Total
Bottle Total |  |  |  | 119
Clipboard/Forms | (blank) | (blank) |  | 1
|  |  | (blank) | 8
|  | (blank) Total |  | 9
| (blank) Total |  |  | 9
Clipboard/Forms Total |  |  |  | 9
Gloves (pair) | (blank) | (blank) | (blank) | 92
|  | (blank) Total |  | 92
| (blank) Total |  |  | 92
Gloves (pair) Total |  |  |  | 92
Instructions | (blank) | (blank) | (blank) | 9
|  | (blank) Total |  | 9
| (blank) Total |  |  | 9
Instructions Total |  |  |  | 9
Item | Container/Size | Preservative | Analysis 1 | 0
|  | Preservative Total |  | 0
| Container/Size Total |  |  | 0
Item Total |  |  |  | 0
Labels | (blank) | (blank) |  | 1
|  |  | (blank) | 8
|  | (blank) Total |  | 9
| (blank) Total |  |  | 9
Labels Total |  |  |  | 9
Packing List | (blank) | (blank) | (blank) | 9
|  | (blank) Total |  | 9
| (blank) Total |  |  | 9
Packing List Total |  |  |  | 9
Temperature Probe | (blank) | (blank) | (blank) | 8
|  | (blank) Total |  | 8
| (blank) Total |  |  | 8
Temperature Probe Total |  |  |  | 8
(blank) | (blank) | (blank) | (blank)
(blank) Total
(blank) Total
(blank) Total
Grand Total |  |  |  | 255

## sample_types
Test | Spring_Analysis | Summer_Analysis
Dissolved metals | SGS North America | SGS North America
Total metals | SGS North America | SGS North America
Total Phosphorous | SGS North America | SGS North America
Nitrogen | SGS North America | SGS North America
BTEX (hydrocarbons) | NONE | SGS North America
TSS | Soldotna Water Quality Tx Plant | Soldotna Water Quality Tx Plant
Fecal coliform | Soldotna Water Quality Tx Plant | Tauriainen

## sample_day_info
Info Category | Parameter | Value | Notes
Environmental | High Tide May 2 | 3:08 | 18.1 ft
Environmental | Low Tide May 2 | 10:23 | 1.9 ftt
Sampling Sites | Metals sampling sites |  | collect at and below RM 30 only

## training_notes
Remind and prep to collect intrinsic parameters
Duplicate samples rotate among sites and teams
Drop off coolers if passing by KWF office

## spring_crew_assignments
Spring 2023 Kenai River Water Quality Sampling Crews Status 3/24/2023
River Mile | Location / Sample Name | Mainstem | Tributary | Samplers/Teams | Confirmed Spring 5/2/2023 | Notes | responded to 3/27/23 formal letter | Confirmed calendar invite
0 | No Name Creek |  | x | Yvonne Weber (Salamatof); Cathy Cline (CIAA Retired); Nick Jacuk (UAF) | x | RM0 has metals field blank
1.5 | Kenai City Dock-DUP | x
1.5 | Kenai City Dock | x
6.5 | Cunningham Park | x |  | KWF (Sara Aamodt, Bonnie Bernard); TTCD (Andy Wizik); KWF (David Wartinbee) | x | Volunteer boat & driver available from KWF. RM 12.5 has metals field blank | DW, AW, SA
10 | Beaver Creek |  | x
10.1 | Kenai River | x
12.5 | Pillars | x
18 | Poachers Cove | x
19 | Slikok Creek |  | x | KPB (Samantha Lopez & Sandra Fletcher); Tiffany Brand (KSWCD) | x |  | SL | TB, SF
21 | Soldotna Bridge | x
22 | Soldotna Creek |  | x
23 | Swiftwater Park | x
30 | Funny River |  | x | CIAA (Emily Heale & Crew); Kenaitze (Moses Jordan + Intern) | x |  | EH | MJ
31 | Funny River - DUP |  | x
31 | Morgan’s Landing | x
36 | Moose River |  | x
40 | Bing’s Landing | x |  | KWF (Brandon Drzazgowski, John Bryan); & AK State Parks (Avery Hanson) | x | AK State Parks providing boat & driver | BD | CN
43 | Upstream of Dow Island | x
44 | Mouth of Killey River |  | x
50 | Skilak Lake Outflow | x
70 | Jim’s Landing | x |  | USFS (Heather Thamm, Alex Palombo & Crew) | x | possibly add Julianne Wilson (Kenaitze) here; | AP
74 | Russian River |  | x |  |  | ak.julianne98@gmail.com
79.5 | Juneau Creek |  | x
82 | Kenai Lake Bridge | x

## property_owners
River Mile | Location / Sample Name | Property Owner | Notes
44 | Mouth of Killey River | CIRI | CIRI has extensive process to request land access. Check out in-person weekend of 4/22/23
43 | Above Dow Island | Reflections Kenai Riverfront Cabins | 34122 Fishermans Rd, Soldotna, AK 99669. Talked to owner, Greg, they know we are coming by | 205-270-6356 | Alternative: On N Shore of bank, Kenai Keys rd. Park near 60.492161340122976, -150.6247232014074; short bushwhack, might be steep bluff
10 | Beaver Creek | Foster's Alaska Cabins | Looks muddy. Spoke with Owner Jason Foster, says access anytime
10.1 | Kenai River |  | best option might be to float down beaver creek to mouth (from foster's), then walk upriver on mainstem to sample, then float downstream to the DNR parcel … or call harding's kenai river lodge

## summer_crew_assignments
--> Move this info to new summer 2023 workbook when available
Spring 2023 Water Quality Sampling Crews
| River Mile | Location / Sample Name | Mainstem | Tributary | Samplers/Teams | Confirmed Summer | Notes
| 0 | No Name Creek |  | x | KPB (Samantha Lopez + Morgan Aldridge), Salamatof (Yvonne Weber) | Yvonne
| 1.5 | Kenai City Dock-DUP | x
| 1.5 | Kenai City Dock | x
| 6.5 | Cunningham Park | x |  | USFWS (Kyle Graham + crew)
| 10 | Beaver Creek |  | x
| 10.1 | Kenai River | x
| 12.5 | Pillars | x
| 18 | Poachers Cove | x
| 19 | Slikok Creek |  | x | ADFG (Kaitlyn Cafferty & ?) |  | rotate a dup to this crew; last of day
| 21 | Soldotna Bridge | x
| 22 | Soldotna Creek |  | x
| 23 | Swiftwater Park | x
| 30 | Funny River |  | x | CIAA (Andy Wizik, Cathie Cline) | x
| 31 | Morgan’s Landing | x
| 36 | Moose River | x
| 36 | Moose River-DUP |  | x
| 40 | Bing’s Landing | x |  |  | ADEC | Need boat
| 43 | Upstream of Dow Island | x
| 44 | Mouth of Killey River |  | x
| 50 | Skilak Lake Outflow | x
| 70 | Jim’s Landing | x |  | USFS (Heather Thamm + Alex Palombo) | x
| 74 | Russian River |  | x
| 79.5 | Juneau Creek |  | x
| 82 | Kenai Lake Bridge | x
<- figure out how to rotate DUPs

## random_site_assigner
site | random_num | sort_num | metals_field_blank | Methods for choosing a random row: https://www.statology.org/random-sample-google-sheets/
RM 10.1 - Kenai River | 0.92852 | 0.019199 | Y | 4/19/2023: decided to reassign RM 10.1 field blank to Pillars (RM12.5), unclear if 10.1 will be acessible
RM0 | 0.34543 | 0.1272 | Y
RM1.5-DUP | 0.86778 | 0.13199
RM 21 - Soldotna Bridge | 0.31058 | 0.14535
RM 10 - Beaver Creek | 0.87266 | 0.14837
RM 22 - Soldotna Creek | 0.27987 | 0.20352
RM 19 - Slikok Creek | 0.19378 | 0.27319
RM 18 - Poachers Cove | 0.38656 | 0.27911
RM1.5 | 0.86177 | 0.30616
RM 23 - Swiftwater Park | 0.0017005 | 0.58408
RM 30 - Funny River | 0.27472 | 0.76277
RM 6.5 - Cunningham Park | 0.35911 | 0.80991
RM 12.5 - Pillars | 0.37211 | 0.9877